## SRS
Date | Updates | Version_No. | Approved by | Link
2026-01-21 | 1. Project Goal: The primary objective was to develop a functional 32-bit x86 operating system kernel capable of running within the QEMU emulator. 2. Core Components: It identified six essential OS areas for implementation: the Kernel, Memory Management, Process Scheduling, Filesystem, Inter-Process Communication (IPC), and a Command-line Shell. 3. Operating Environment: It specified that the software would interact with virtualized hardware (VGA display, PS/2 keyboard, and PIT) using x86 Assembly and Memory Mapped I/O (MMIO). 4. Basic Scheduling: The process scheduler was broadly defined as a mechanism for task switching with "low latency". 5. Initial Security and Safety: It established baseline requirements that user programs must not be able to crash the kernel or modify kernel code without admin permission. 6. Visual Documentation: It provided a high-level UML Class Diagram and a Sequence Diagram showing basic interactions between the Kernel, Scheduler, Memory Manager, and Drivers. | 1 | Alpha Managers (Ved MItra Verma, Taksh Mehta, Maynk Tiwari, Aditya Sharma) | https://drive.google.com/drive/folders/1Smez2xUyXLgTf2Rgfg-16WEfzbgaC08P?usp=sharing
2026-02-04 | 1. Core Architectural Foundation While Version 1.0 described Mini OS as a "self-contained product" not based on existing systems , Version 2.0 pivotally redefines it as an extension of the xv6 teaching operating system originally developed at MIT. This shift changes the project's scope from building a kernel from scratch to modifying an established 32-bit Unix-like environment. Version 2.0 also adds a clear pedagogical goal, emphasizing the demonstration of fundamental OS concepts through modular design rather than production-level completeness. 2. Advanced Process Scheduling The scheduling requirements evolved from a simple "task switching" description in Version 1.0 to a sophisticated priority-based preemptive algorithm in Version 2.0. The new version details dynamic priority adjustments, where system and foreground processes receive higher base priorities. Notably, it introduces "aging" to prevent process starvation and "penalties" for processes that monopolize the CPU, ensuring much more granular control over multitasking fairness. 3. Memory Management and Copy-On-Write Version 2.0 significantly expands the memory management subsystem by introducing Copy-On-Write (COW) optimization during the fork() system call. While Version 1.0 focused on basic memory mapping , Version 2.0 specifies the use of paging to eliminate external fragmentation and provide strict memory isolation through per-process virtual address spaces. It also adds detailed stimulus/response sequences for handling page faults caused by COW violations or absent pages. 4. Inter-Process Communication (IPC) IPC was only briefly mentioned as a "communications interface" in the first version. In Version 2.0, it is elevated to a core system feature with a "MEDIUM" priority. The updated requirements specify both message-based IPC using kernel-managed mailboxes and shared memory for high-performance data exchange. It also mandates that the kernel must enforce strict access permissions and size limits to prevent processes from compromising system security. 5. Project Management and Team Roles Version 2.0 introduces a formal organizational structure that was entirely absent in Version 1.0. It names four "Alpha Managers" with specific responsibilities for software systems, requirements, and stakeholders. Additionally, the update incorporates a Tentative Sprint Plan—allocating eight weeks across scheduling, memory, and IPC —and identifies a modern toolset including Trello, Notion, and Git for collaboration and version control. 6. Technical Documentation and UML The visual and formal documentation saw the most dramatic increase in volume. Version 2.0 replaced the single, basic class diagram of Version 1.0 with a comprehensive suite of eight different UML diagrams, including Composite, Component, Activity, Sequence, Timing, and Deployment diagrams. Furthermore, it established a strict Design and Coding Template, mandating specific naming conventions like Pascal_Snake_Case for modules and lowercase_snake_case for functions to ensure codebase maintainability. | 2 | Alpha Managers (Ved MItra Verma, Taksh Mehta, Maynk Tiwari, Aditya Sharma)
2026-03-02 | 1. Formalized Functional Requirements: Version 3.0 introduces a rigorous identification system for requirements, utilizing unique labels such as REQ-SCH-N, REQ-MEM-N, and REQ-IPC-N to ensure traceability across the development lifecycle. Unlike the broad descriptions in Version 2.0, this version provides granular functional mandates, such as specific paging constraints like the fixed 4096-byte page size and the maximum allowed capacity for kernel-managed mailboxes. 2. Detailed Sprint Planning and Feature Ownership: A significant addition in Version 3.0 is the comprehensive MiniOS Sprint Plan, which breaks down development into four distinct one-week sprints. This plan assigns specific feature ownership: Taksh Mehta leads the Dynamic Priority Scheduler, Aditya Sharma and Mayank Tiwari manage Paging and COW, and Ved Mitra Verma handles Hybrid IPC. Each sprint now has defined weekly goals and individual tasks, transitioning from a tentative timeline to a tactical execution phase. 3. Mathematical and Logic Models: Version 3.0 adds formal mathematical notations to define the behavior of critical subsystems, providing a level of precision absent in previous versions. The document now includes a specific priority update rule for the scheduler using aging (alpha) and CPU penalty (beta) parameters, a memory model for calculating Copy-On-Write overhead, and a structural model for Hybrid IPC. 4. Advanced System Feature Specifications: Core features have been expanded with technical depth, such as the scheduling subsystem explicitly specifying Dynamic Priority-Based Scheduling with Aging. The memory management section now details specific x86 PTE layouts and reference counting required for COW. Similarly, the IPC section defines the "Hybrid" nature of the system—combining mailboxes for message passing with shared memory regions for high-performance data transfer. 5. Risk Management and Non-functional Requirements: Version 3.0 introduces a Risk Register that identifies potential technical hurdles, such as COW race conditions on reference counts or IPC isolation bugs, along with mitigation strategies. Furthermore, non-functional requirements have been quantified; for example, the COW mechanism is required to reduce physical memory duplication by at least 30%. It also emphasizes safety requirements, ensuring that invalid shared memory access returns an error code rather than causing a kernel panic. 6. Enhanced Modeling and Appendices: The UML modeling section has been moved to the Appendices and bolstered with detailed technical diagrams. While Version 2.0 contained basic diagrams, Version 3.0 includes complex Sequence Diagrams illustrating the COW page fault flow, Composite Diagrams showing the internal kernel structure, and a Deployment Diagram mapping the relationship between the Host Machine, QEMU, and the MiniOS Kernel. | 3 | Alpha Managers (Ved MItra Verma, Taksh Mehta, Maynk Tiwari, Aditya Sharma)
2026-03-12 | 1. Feature Scope Pivot and Deprecations Version 4.0 fundamentally alters the project scope by completely removing the Inter-Process Communication (IPC) and Shared Memory features. In their place, the system introduces three new core subsystems: a File Management System (responsible for file storage, access, and deletion), a Garbage Collector (to automatically reclaim memory from deleted files), and Dynamic Memory Compaction (to eliminate memory fragmentation). 2. Team Role Realignment To support the new architectural direction, the Sprint Plan and feature ownership have been significantly updated. Ved Mitra Verma transitions from handling Hybrid IPC to managing the File Manager and Garbage Collector. Mayank Tiwari's responsibilities pivot from supporting Paging to leading the Dynamic Memory and Compaction integration. 3. Formalized Functional Requirements Overhaul The document strips all previously established IPC requirements (REQ-IPC-N). It introduces entirely new functional requirement tracks: REQ-FILE-1 through REQ-FILE-4 for file operations, REQ-GC-1 through REQ-GC-3 mandating memory reclamation during idle system states, and REQ-DMEM-1 through REQ-DMEM-3 for restructuring memory to reduce fragmentation upon file deletion. 4. Non-Functional Requirements (NFR) Adjustment Performance and safety metrics have been recalibrated to match the new scope. The IPC message delivery latency requirement was removed and replaced with a new performance mandate (NFR-PERF-3) stating that memory compaction must actively reduce fragmentation. Safety requirements were broadened to safely trap any invalid memory access, rather than specifically focusing on shared memory isolation. 5. Comprehensive UML Redesign The system's visual architecture was entirely rewritten to reflect the new subsystems. The Class, Component, and Composite diagrams completely replaced IPC modules with FileManager, GarbageCollector, and MemoryCompactor, mapping them directly to the MemoryManager. The Activity and Sequence diagrams shifted from visualizing a fork() and IPC flow to detailing a full "Process Execution Sequence" that includes I/O requests, file reads/writes, and triggering garbage collection and memory compaction when memory becomes fragmented. The Use Case diagram similarly deprecated messaging actions in favor of file manipulation and memory maintenance tasks. | 4 | Alpha Managers (Ved MItra Verma, Taksh Mehta, Maynk Tiwari, Aditya Sharma)

## Alpha Card
Date | Alpha Concern | Alpha Card | Current Card | Status | Notes to support status | Approved by | Alpha | Alpha Manager
| Customer / Solution / Endeavor | Opportunity / Stakeholder / Requirements / Software System / Team / Work / Way of Working | 1 / 2 / ... | Which points completed in current card |  | Alpha manager | Stakeholder | Mayank Tiwari (B24CS1098)
2026-01-21 | Customer | Opportunity | Identified (1/6) | Idea behind opportunity defined , At least one investing stakeholder interested , other stakeholders identified | Refer to SRS | Aditya Sharma (B24CS1119) | Opportunity | Aditya Sharma (B24CS1119)
|  | Stakeholders | Recognized (1/6) | Stakeholder groups identified; Key stakeholders represented; Responsibilities broadly defined | Refer to SRS | Mayank Tiwari (B24CS1098) | Requirements | Mayank Tiwari (B24CS1098)
| Solution | Requirements | Bounded (2/6) | Development stakeholders identified; System purpose agreed; Success clear; Shared understanding exists; Format agreed; Constraints identified; Assumptions clear | Refer to SRS | Mayank Tiwari (B24CS1098) | Software System | Mehta Ashish Taksh (B24CS1115)
|  | Software System | Architecture Selected (1/6) | Architecture criteria agreed; HW platform identified (x86); Technologies selected; System boundary known; Organization decisions made; Core subsystems defined | Refer to SRS | Mehta Ashish Taksh (B24CS1115) | Team | Mehta Ashish Taksh (B24CS1115)
| Endeavour | Work | Initiated (1/6) | Required result clear; Constraints clear; Initiator identified; Accepting stakeholders known; Priority clear | Refer to SRS | Ved Mitra Verma (B24CS1086) | Work | Ved Mitra Verma (B24CS1086)
|  | Team | Seeded (1/5) | Mission defined; Constraints known; Responsibilities outlined; Required competencies identified | Refer to SRS | Mehta Ashish Taksh (B24CS1115) | Way of Working | Ved Mitra Verma (B24CS1086)
|  | Way of Working | Principles Established (1/6) | Development intent clear; Technical approach understood | Refer to SRS | Ved Mitra Verma (B24CS1086)
2026-02-04 | Customer | Stakeholders | Recognized (1/6) + Represented (2/6) | Recognized: - Stakeholder groups identified - Key stakeholder groups represented - Responsibilities defined Represented: - Responsibilities agreed - Representatives authorized - Collaboration approach agreed - Way of working supported & respected | The SRS explicitly identifies stakeholder-facing roles and responsibilities through the Alpha Managers section, where different members are assigned responsibility for stakeholder, opportunity, team, and way of working. It also shows that stakeholder concerns have been reflected in the project scope, requirements, and priorities, which supports that key stakeholder groups have been identified and represented. | Mayank Tiwari (B24CS1098)
|  | Opportunity | Identified (1/6) + Solution Needed (2/6) | Identified: - Idea behind opportunity identified - At least one investing stakeholder interested - Other stakeholders identified Solution Needed: - Problem understood - Solution approach identified - Stakeholders agree solution is needed - Constraints understood | The SRS clearly states the opportunity behind MiniOS as an educational operating system built on xv6 to demonstrate core OS concepts like scheduling, paging, and IPC in a modular and understandable way. It also defines the need for the solution by identifying the problem space, expected learning goals, system scope, constraints, and intended users such as students and system programmers. | Aditya Sharma (B24CS1119)
| Solution | Requirements | Conceived (1/6) + Bounded (2/6) | Conceived: - Opportunity addressed by requirements - Basic requirements identified - Stakeholders agree system is worth pursuing Bounded: - Development stakeholders identified - System purpose agreed - System success clear - Shared solution understanding exists - Requirements' format agreed - Requirements management in place - Prioritization scheme clear - Constraints identified & considered - Assumptions clear | The SRS provides a clear and structured requirements baseline through functional requirements for scheduling, memory management, and IPC, along with priority labels such as HIGH and MEDIUM. It also bounds the solution by defining scope, assumptions, dependencies, operating environment, implementation constraints, and a shared naming/design convention, showing that the system purpose, success direction, and requirement structure are agreed. | Mayank Tiwari (B24CS1098)
|  | Software System | Architecture Selected (1/6) | Architecture Selected: - Architecture selection criteria agreed - HW platforms identified - Technologies selected - System boundary known - Decisions on system organization made - Buy, build, reuse decisions made - Key technical risks agreed to | The SRS identifies the architectural basis of the system as an xv6-based kernel running in QEMU on x86, with key subsystem decomposition into Scheduler, Memory Manager, and IPC. The UML diagrams and component/composite diagrams further show system organization, interfaces, and major design decisions, which supports that architecture selection criteria, technologies, system boundary, and technical structure have been decided. | Mehta Ashish Taksh (B24CS1115)
| Endeavour | Work | Initiated (1/6) + Prepared (2/6) | Initiated: - Required result clear - Constraints clear - Funding stakeholders known - Initiator identified - Accepting stakeholders known - Source of funding clear - Priority clear Prepared: - Work planned - Resources available - Schedule defined - Risks identified | The work is initiated because the SRS defines the required result, project scope, constraints, and priorities. It is prepared because the document includes a tentative sprint plan for scheduling, memory management, and IPC, and it specifies the project management tools to be used, including Trello, Notion, Git, QEMU, and the GNU toolchain, showing planning, scheduling, and resource readiness. | Ved Mitra Verma (B24CS1086)
|  | Team | Seeded (1/5) + Formed (2/5) | Seeded: - Mission defined - Constraints known and defined - Growth mechanisms in place - Composition defined - Responsibilities outlined - Required commitment level clear - Required competencies identified - Size determined - Governance rules defined - Leadership model selected Formed: - Team members available - Roles accepted - Communication started - Initial working agreements made | The SRS shows the team has been seeded and formed because members are explicitly named, alpha manager responsibilities are distributed, and roles are aligned to different concern areas such as stakeholder, opportunity, team, and way of working. This demonstrates defined mission support, outlined responsibilities, selected leadership/ownership, and accepted participation by team members. | Mehta Ashish Taksh (B24CS1115)
|  | Way of Working | Principles Established (1/6) + Foundation Established (2/6) | Principles Established: - Team actively support principles - Stakeholders agree with principles - Tool needs agreed - Approach recommended - Operational context understood - Practice & tool constraints known Foundation Established: - Key practices & tools selected - Practices needed to start work agreed - Non-negotiable practices & tools identified - Gaps between available and needed way of working understood - Gaps in capability understood - Integrated way of working available | The SRS establishes the way of working by defining project management tools, version control, documentation approach, coding and naming conventions, and the use of QEMU for controlled testing. The revision history, sprint plan, and design/coding template show that key practices, tools, and collaboration foundations are already selected and agreed, which supports both principles established and foundation established. | Ved Mitra Verma (B24CS1086)
2026-03-02 | Customer | Stakeholders | Recognized (1/6) + Represented (2/6) + Involved (3/6) | Recognized: - Stakeholder groups identified - Key stakeholder groups represented - Responsibilities defined Represented: - Responsibilities agreed - Representatives authorized - Collaboration approach agreed - Way of working supported & respected Involved: - Representatives assist the team - Timely feedback and decisions provided - Changes promptly communicated | Stakeholders are clearly identified in the Intended Audience section (developers, evaluators, testers, supervisors) and responsibilities are explicitly assigned via the Alpha Managers section (page 6). Representation is ensured through role ownership and responsibility mapping. Additionally, stakeholders are involved through continuous interaction in development via sprint planning, feature ownership, and coordination points (e.g., shared work on COW and integration tasks), showing active participation and feedback flow during execution. | Mayank Tiwari (B24CS1098)
|  | Opportunity | Identified (1/6) + Solution Needed (2/6) + Value Established (3/6) | Identified: - Idea behind opportunity identified - At least one investing stakeholder interested - Other stakeholders identified Solution Needed: - Problem understood - Solution approach identified - Stakeholders agree solution is needed - Constraints understood Value Established: - Opportunity value quantified - Solution impact understood - System value understood - Success criteria clear - Outcomes clear and quantified | The opportunity is identified in the Purpose and Product Scope sections as building a pedagogical OS using xv6 (page 5). The need for the solution is established through clearly defined OS problems (scheduling, paging, IPC) and target users (students, developers). Value is further established through measurable goals such as conceptual clarity, correctness, and performance requirements like bounded waiting time and memory optimization (page 14), which quantify system impact and expected outcomes. | Aditya Sharma (B24CS1119)
| Solution | Requirements | Conceived (1/6) + Bounded (2/6) + Coherent (3/6) | Conceived: - Opportunity addressed by requirements - Basic requirements identified - Stakeholders agree system is worth pursuing Bounded: - Development stakeholders identified - System purpose agreed - System success clear - Shared solution understanding exists - Requirements' format agreed - Requirements management in place - Prioritization scheme clear - Constraints identified & considered - Assumptions clear Coherent: - Requirements shared - Requirements' origin clear - Rationale clear - Conflicts addressed - Essential characteristics clear - Key usage scenarios explained - Priorities clear - Impact understood - Team knows & agrees on what to deliver | Refer to SRS | Mayank Tiwari (B24CS1098)
|  | Software System | Architecture Selected (1/6) | Architecture Selected: - Architecture selection criteria agreed - HW platforms identified - Technologies selected - System boundary known - Decisions on system organization made - Buy, build, reuse decisions made - Key technical risks agreed to | Refer to SRS | Mehta Ashish Taksh (B24CS1115)
| Endeavour | Work | Initiated (1/6) + Prepared (2/6) | Initiated: - Required result clear - Constraints clear - Funding stakeholders known - Initiator identified - Accepting stakeholders known - Source of funding clear - Priority clear Prepared: - Work planned - Resources available - Schedule defined - Risks identified | Refer to SRS | Ved Mitra Verma (B24CS1086)
|  | Team | Seeded (1/5) + Formed (2/5) + Collaborating (3/5) | Seeded: - Mission defined - Constraints known and defined - Growth mechanisms in place - Composition defined - Responsibilities outlined - Required commitment level clear - Required competencies identified - Size determined - Governance rules defined - Leadership model selected Formed: - Team members available - Roles accepted - Communication started - Initial working agreements made Collaborating: - Works as one unit - Communication open and honest - Focused on mission - Members know each other | Refer to SRS | Mehta Ashish Taksh (B24CS1115)
|  | Way of Working | Principles Established (1/6) + Foundation Established (2/6) | Principles Established: - Team actively support principles - Stakeholders agree with principles - Tool needs agreed - Approach recommended - Operational context understood - Practice & tool constraints known Foundation Established: - Key practices & tools selected - Practices needed to start work agreed - Non-negotiable practices & tools identified - Gaps between available and needed way of working understood - Gaps in capability understood - Integrated way of working available | Refer to SRS | Ved Mitra Verma (B24CS1086)
2026-03-16 | Customer | Opportunity | Identified + Solution Needed + Value Established + Viable | Identified: - Idea behind opportunity identified - At least one investing stakeholder interested - Other stakeholders identified Solution Needed: - Problem understood - Solution approach identified - Stakeholders agree solution is needed - Constraints understood Value Established: - Opportunity value quantified - Solution impact understood - System value understood - Success criteria clear - Outcomes clear and quantified Viable: - Solution outlined - Solution possible within constraints - Risks acceptable & manageable - Solution profitable - Reasons to develop solution understood - Pursuit viable | Refer to SRS | Aditya Sharma (B24CS1119)
|  | Stakeholders | Recognized + Represented + Involved + In Agreement | Recognized: - Stakeholder groups identified - Key stakeholder groups represented - Responsibilities defined Represented: - Responsibilities agreed - Representatives authorized - Collaboration approach agreed - Way of working supported & respected Involved: - Representatives assist the team - Timely feedback and decisions provided - Changes promptly communicated In Agreement: - Stakeholders actively support the system - Agreement on system direction - Conflicts resolved | Refer to SRS | Mayank Tiwari (B24CS1098)
| Solution | Requirements | Conceived + Bounded + Coherent | Conceived: - Opportunity addressed by requirements - Basic requirements identified - Stakeholders agree system is worth pursuing Bounded: - Development stakeholders identified - System purpose agreed - System success clear - Shared solution understanding exists - Requirements' format agreed - Requirements management in place - Prioritization scheme clear - Constraints identified & considered - Assumptions clear Coherent: - Requirements shared - Requirements' origin clear - Rationale clear - Conflicts addressed - Essential characteristics clear - Key usage scenarios explained - Priorities clear - Impact understood - Team knows & agrees on what to deliver | Refer to SRS | Mayank Tiwari (B24CS1098)
|  | Software System | Architecture Selected + Demonstrable | Architecture Selected: - Architecture selection criteria agreed - HW platforms identified - Technologies selected - System boundary known - Decisions on system organization made - Buy, build, reuse decisions made - Key technical risks agreed to Demonstrable: - Key architectural characteristics demonstrated - System exercised & performance measured - Critical HW configurations demonstrated - Critical interfaces demonstrated - Integration with environment demonstrated - Architecture accepted as fit-for-purpose | Refer to SRS | Mehta Ashish Taksh (B24CS1115)
| Endeavour | Work | Initiated + Prepared + Started | Initiated: - Required result clear - Constraints clear - Funding stakeholders known - Initiator identified - Accepting stakeholders known - Source of funding clear - Priority clear Prepared: - Work planned - Resources available - Schedule defined - Risks identified Started: - Development started - Progress monitored - Definition of done in place - Tasks being progressed | Refer to SRS | Ved Mitra Verma (B24CS1086)
|  | Team | Seeded + Formed + Collaborating | Seeded: - Mission defined - Constraints known and defined - Growth mechanisms in place - Composition defined - Responsibilities outlined - Required commitment level clear - Required competencies identified - Size determined - Governance rules defined - Leadership model selected Formed: - Team members available - Roles accepted - Communication started - Initial working agreements made Collaborating: - Works as one unit - Communication open and honest - Focused on mission - Members know each other | Refer to SRS | Mehta Ashish Taksh (B24CS1115)
|  | Way of Working | Principles Established + Foundation Established + In Use | Principles Established: - Team actively support principles - Stakeholders agree with principles - Tool needs agreed - Approach recommended - Operational context understood - Practice & tool constraints known Foundation Established: - Key practices & tools selected - Practices needed to start work agreed - Non-negotiable practices & tools identified - Gaps between available and needed way of working understood - Gaps in capability understood - Integrated way of working available In Use: - Practices & tools in use - Regularly inspected - Adapted to context - Supported by team - Feedback mechanisms in place - Practices & tools support collaboration | Refer to SRS | Ved Mitra Verma (B24CS1086)

## UML
Date | Diagram Category | Updates | Version_No. | Approved by | Link
2026-01-21 | Class Diagram | Initial architectural draft defining basic Kernel, MemoryManager, Scheduler, Filesystem, and Driver classes. | 1 | Alpha Managers | https://drive.google.com/drive/folders/1pkY0PuBBHM46Bz8wuN9j9K_eK7VKUknF?usp=sharing
2026-01-21 | Sequence Diagram | Preliminary flow showing high-level interaction between the Kernel and major subsystems like VGA and Keyboard drivers. | 1 | Alpha Managers
2026-02-04 | Class Diagram | Refined relationships showing specific process attributes like pagetable_t and parent pointers. | 2 | Alpha Managers
2026-02-04 | Composite Diagram | Introduced a modular view of the xv6 Kernel structure, separating Process Management from Memory and IPC. | 2 | Alpha Managers
2026-02-04 | Component Diagram | Visualized core CPU dependencies on the Scheduler, Memory Manager, and IPC components. | 2 | Alpha Managers
2026-02-04 | Use Case Diagram | Defined basic user interactions including process creation, memory allocation, and IPC communication. | 2 | Alpha Managers
2026-02-04 | Activity Diagram | Mapped the standard fork() lifecycle from PCB allocation to resource freeing upon exit. | 2 | Alpha Managers
2026-02-04 | Sequence Diagram | Detailed the timer interrupt mechanism for context switching between Process A and Process B. | 2 | Alpha Managers
2026-02-04 | Timing Diagram | Visualized state transitions (Running, Ready, Blocked) for concurrent processes over a nanosecond timeline. | 2 | Alpha Managers
2026-02-04 | Deployment Diagram | Defined the execution environment mapping the xv6 Kernel subsystems within the QEMU Emulator. | 2 | Alpha Managers
2026-03-02 | Class Diagram | Finalized with technical methods for Copy-On-Write (cow_copy_page) and reference counting (inc_refcount). | 3 | Alpha Managers
2026-03-02 | Activity Diagram | Enhanced logic showing specific decision points for IPC reception and shared memory blocking states. | 3 | Alpha Managers
2026-03-02 | Component Diagram | Refined interaction flow specifically showing memory requests triggering page faults within the Memory Manager. | 3 | Alpha Managers
2026-03-02 | Composite Diagram | Detailed internal kernel signaling where the Timer uses ticks to trigger Scheduler state transitions. | 3 | Alpha Managers
2026-03-02 | Deployment Diagram | Expanded to include the Host Machine relationship and the GNU Toolchain (gcc, ld, make) loading the kernel. | 3 | Alpha Managers
2026-03-02 | Sequence Diagram | Added a dedicated technical flow for Copy-On-Write Write Operations and page duplication logic. | 3 | Alpha Managers
2026-03-02 | Use Case Diagram | Formalized kernel-level use cases including specific "Include" relationships for Context Switches and Page Faults. | 3 | Alpha Managers
2026-03-02 | Timing Diagram | Re-validated process state transitions to align with the finalized Dynamic Priority-Based Scheduling parameters. | 3 | Alpha Managers
2026-03-12 | Class Diagram | Removed the IPC, Shared_Memory_Manager, and Process_Memory_Manager classes. Added new core classes to reflect the V4 features: GarbageCollector, MemoryCompactor, FileManager, File, PriorityQueue, and CPUManager. | 4 | Alpha Managers
2026-03-12 | Component Diagram | Removed the IPC Manager component. Added FileManager, MemoryCompactor, and GarbageCollector components. Introduced explicit provided/required interfaces (e.g., IScheduling, IFile, IMemory) connecting these components. | 4 | Alpha Managers
2026-03-12 | Composite Diagram | Replaced the internal IPC and Timer linkages with new structural logic mapping the GarbageCollector (reclaimMemory()) and MemoryCompactor (compactMemory()) directly to the MemoryManager. | 4 | Alpha Managers
2026-03-12 | Deployment Diagram | Inside the MiniOS Kernel node, the IPC Manager and Process Manager nodes were swapped out. They were replaced with FileManager, GarbageCollector, and CPUManager nodes running on the QEMU Emulator. | 4 | Alpha Managers
2026-03-12 | Activity Diagram | Completely redesigned. The diagram transitioned from a fork() and IPC-centric flow to a "MiniOS Process Execution Activity" flow. It now traces an arithmetic process execution that terminates with checks for memory fragmentation, triggering the Garbage Collector and Memory Compaction. | 4 | Alpha Managers
2026-03-12 | Sequence Diagram | Replaced the previous Copy-On-Write (COW) page fault operation flow. The new "Process Execution Sequence" details the full lifecycle interactions with the IOManager, FileManager (read/write file), and GarbageCollector (reclaim memory). | 4 | Alpha Managers
2026-03-12 | Use Case Diagram | Removed all IPC-related use cases, such as "Send Message", "Receive Message", and "Allocate Shared Memory". Added explicit new use cases for the user/system: "Create File", "Delete File", "Run Garbage Collector", and "Perform Memory Compaction". | 4 | Alpha Managers
2026-03-12 | Timing Diagram | No structural changes were made. It retains the identical state transition timelines (Ready, Blocked, Running) across a nanosecond scale for Process A and Process B. | 4 | Alpha Managers

## Implementation
Attribute | Requirements (Functional / Non-functional / Business) | Component | Class | Key Attributes | Functions | Start Date of Code | End Date of Code | Update Date | Update Made | Reason for Update | Team Member(s) Designing / Updating Code | Test / Integration Status Details |  | Link
[12 empty] | Test ID | Complete / Ongoing / Abandoned | Github link: | https://github.com/Ved-Mitra/miniOS-Design
Description | These requirement come from the SRS sections | The component name that solves the requirements | The list of classes within the component that apply to the requirements |  | The list of functions per class that apply to the requirements; | Some format can be followed [mm/dd/yyyy] etc. |  |  | These can be code_changes / integrations / etc |  |  |  |  | Testing Folder Link: | https://drive.google.com/drive/folders/1-Qy8upMlD4u3B3dBqn6nPsdiafUeymJk?usp=sharing
Refer to SRS | Functional | Process Scheduling | CPU | int apicid; struct context* scheduler; struct proc* proc | scheduler() | 2026-03-03 | 2026-03-08 |  | Replaced round-robin with priority-based selection |  | Taksh | TC_F_GC_1 | Completed
| Functional | Process Scheduling | CPU | int apicid; struct context* scheduler; struct proc* proc | context_switch() | 2026-03-03 | 2026-03-08 |  | No change from xv6 base |  | Taksh | TC_F_GC_2 | Completed
| Functional | Process Scheduling | Scheduler | struct proc* chosen; struct proc ptable[] | schedule() | 2026-03-03 | 2026-03-08 |  | Added highest-priority RUNNABLE selection loop |  | Taksh | TC_SCH_1 | Completed
| Functional | Process Scheduling | Scheduler | struct proc* chosen; struct proc ptable[] | yield() | 2026-03-04 | 2026-03-05 |  | No change from xv6 base |  | Taksh | TC_CoW_1 | Completed
| Functional | Process Scheduling | Scheduler | struct proc* chosen; struct proc ptable[] | sleep() | 2026-03-05 | 2026-03-06 |  | No change from xv6 base |  | Taksh | TC_MEM_ALLOC_1 | Ongoing
| Functional | Process Scheduling | Scheduler | struct proc* chosen; struct proc ptable[] | update_priority() | 2026-03-10 | 2026-03-12 |  | Beta penalty applied in trap.c on timer tick |  | Taksh | TC_SCH_2 | Ongoing
| Functional | Process Scheduling | Scheduler | struct proc* chosen; struct proc ptable[] | apply_aging() | 2026-03-06 | 2026-03-08 |  | Alpha increment applied in scheduler() once per tick |  | Taksh | TC_MEM_ALLOC_1 | Ongoing
| Functional | Process Scheduling | Scheduler | struct proc* chosen; struct proc ptable[] | apply_cpu_penalty() | 2026-03-12 | 2026-03-14 |  | is_cpu_bound flag set when cpu_ticks > TCPU_MAX |  | Taksh
| Functional | Process Scheduling | Process | int pid; int priority; int wait_ticks; int cpu_ticks; int window_ticks; int is_cpu_bound | fork() | 2026-03-05 | 2026-03-06 |  | Child inherits priority=50 via allocproc() |  | Taksh
| Functional | Process Scheduling | Process | int pid; int priority; int wait_ticks; int cpu_ticks; int window_ticks; int is_cpu_bound | exec() | 2026-03-14 | 2026-03-15 |  | No change from xv6 base |  | Taksh
| Functional | Process Scheduling | Process | int pid; int priority; int wait_ticks; int cpu_ticks; int window_ticks; int is_cpu_bound | exit() | 2026-03-07 | 2026-03-08 |  | No change from xv6 base |  | Taksh
| Functional | Process Scheduling | Process | int pid; int priority; int wait_ticks; int cpu_ticks; int window_ticks; int is_cpu_bound | wait() | 2026-03-08 | 2026-03-10 |  | No change from xv6 base |  | Taksh
| Functional | Process Scheduling | Process | int pid; int priority; int wait_ticks; int cpu_ticks; int window_ticks; int is_cpu_bound | yield() | 2026-03-02 | 2026-03-04 |  | Called after priority update on every timer tick |  | Taksh
| Functional | Process Scheduling | Process | int pid; int priority; int wait_ticks; int cpu_ticks; int window_ticks; int is_cpu_bound | update_state() | 2026-03-02 | 2026-03-04 |  | State transitions: EMBRYO→RUNNABLE→RUNNING→ZOMBIE |  | Taksh
| Functional | Process Scheduling | Trap Handler | struct proc* p; uint ticks; int sched_beta; int sched_tcpu_max; int sched_W | trap() | 2026-03-15 | 2026-03-17 |  | Added cpu_ticks++, window reset, beta penalty on IRQ_TIMER |  | Taksh
| Functional | Process Scheduling | Trap Handler | struct proc* p; uint ticks; int sched_beta; int sched_tcpu_max; int sched_W | sched_tick() | 2026-03-12 | 2026-03-17 |  | Increments cpu_ticks and window_ticks each timer interrupt |  | Taksh
| Functional | Memory Management | Memory_Manager | global allocator state | kinit(),freerange() | 2026-03-03 | 2026-03-08 | - | Initialized memory statistics tracking and integrated page counting during allocator setup. | To maintain a global view of total available physical memory pages and enable future memory management optimizations. | Aditya,Mayank
| Functional | Memory Management | Process_Memory_Manager | struct process* owner | kalloc() | 2026-03-03 | 2026-03-08 | - | Enhanced allocation logic by updating dynamic memory counters (free and allocated pages) during page allocation. | To monitor runtime memory usage and support higher-level features like compaction and memory analysis. | Aditya,Mayank
| Functional | Memory Management | Process_Memory_Manager | struct process* owner | kfree() | 2026-03-03 | 2026-03-08 | - | Modified deallocation logic to update memory tracking counters while safely returning pages to the freelist. | To ensure consistency in memory statistics and maintain accurate tracking of free and allocated pages. | Aditya,Mayank
| Functional | Memory Management | Process_Memory_Manager | struct process* owner | uvm_init() | 2026-03-04 | 2026-03-05 | -
| Functional | Memory Management | Process_Memory_Manager | struct process* owner | uvmalloc() | 2026-03-05 | 2026-03-06 | - | Updated allocation to integrate with reference counting and page mapping | To ensure all allocated pages are tracked and compatible with COW-based memory sharing | Aditya Sharma
| Functional | Memory Management | Process_Memory_Manager | struct process* owner | vmfault() | 2026-03-10 | 2026-03-12 | - | Implemented Copy-On-Write page fault handler | To enable lazy copying of memory pages only upon modification | Aditya Sharma
| Functional | Memory Management | Process_Memory_Manager | struct process* owner | uvmcopy() - modified | 2026-03-06 | 2026-03-08 | - | Modified to share pages instead of copying | To implement memory sharing after fork as required in Copy-On-Write | Aditya Sharma
| Functional | Memory Management | Process_Memory_Manager | struct process* owner | cow handler inside vm.c | 2026-03-12 | 2026-03-14 | - | Added logic to detect write faults on shared pages and trigger duplication | To ensure correct behavior of Copy-On-Write during runtime memory access | Aditya Sharma
| Functional | Memory Management | Process_Memory_Manager | struct process* owner | mappages() | 2026-03-05 | 2026-03-06 | - | Updated to support shared read-only mappings | To enforce write protection required for triggering page faults in COW | Aditya Sharma
| Functional | Memory Management | Process_Memory_Manager | struct process* owner | uvmunmap() | 2026-03-14 | 2026-03-15 | - | Modified to correctly handle reference counts while unmapping pages | To ensure shared pages are not freed incorrectly during deallocation | Aditya Sharma
| Functional | Memory Management | PageTable | entries; int refcount | PTE_FLAGS(*pte) macro | 2026-03-07 | 2026-03-08 | - | Removed write permission (PTE_W cleared) | To maintain correct page table permissions and support safe memory access | Aditya Sharma
| Functional | Memory Management | PageTable | entries; int refcount | *pte &= ~PTE_W (Removing write flag) | 2026-03-08 | 2026-03-10 | - | Cleared write permission bit for shared pages | To force page fault on write access, enabling Copy-On-Write mechanism | Aditya Sharma
| Functional | Memory Management | PageTable | entries; int refcount | ref_count[PA2IDX(pa)]++ | 2026-03-02 | 2026-03-04 | - | Incremented reference count when page is shared between processes | To track number of processes referencing a page | Aditya Sharma
| Functional | Memory Management | PageTable | entries; int refcount | ref_count[PA2IDX(pa)]-- | 2026-03-02 | 2026-03-04 | - | Decremented reference count when a process releases a page | To ensure correct memory reclamation when pages are no longer shared | Aditya Sharma
| Functional | Memory Management | PageTable | entries; int refcount | logic inside kfree() | 2026-03-15 | 2026-03-17 | - | Integrated reference count check before freeing physical memory | To avoid freeing memory still in use by other processes in COW
| Functional | Memory Management | Compact |  | compact_memory() |  |  |  | - | - | Mayank Tiwari
| Functional | File Manager | File | struct file, struct memfile (tracking type, ref_count, read, write, offset, data, size, is_maked_deleted) | filealloc(), fileclose() | 2026-03-02 | 2026-03-10 | 2026-03-08 | added new struct memfile, new file type (FD_MEM) for | To implement the new file structure of in-memory file | Ved Mitra Verma
| Functional | File Manager | SysFile | - | sys_memcreate(), sys_memdelete() | 2026-03-02 | 2026-03-10 | 2026-03-10 | added syscalls for the new in-memory file part | to enable system to call these functions | Ved Mitra Verma
| Functional | File Manager | File | struct file, struct memfile (tracking type, ref_count, read, write, offset, data, size, is_maked_deleted) | filewrite(), fileread() | 2026-03-10 | 2026-03-18 | 2026-03-18 | modified fileread(), filewrite() | modified the fileread(), filewrite() functions for the new file type (FD_MEM) to enable reading andwriting of the new in-memory file structure | Ved Mitra Verma
| Functional | Garbage Collector | GC | mftable | garbage_collect() | 2026-03-12 | 2026-03-16 | 2026-03-16 | added a new file gc.c and new function garbage_collect() | Added the intial structure of garbage collector collects files and frees space | Ved Mitra Verma

## Sprint Plan
SPRINT PLAN :
Sprint | Week | Semester Timline |  | Task / Deliverable | Owner | Status | Date Of Completion | Notes
|  | START | END
1 | 1 |  |  | Foundation & Environment Setup |  | TRUE |  | Goal: Working dev env & stubs
|  |  |  | Study proc.c, trap.c, sched() workflow | Taksh | TRUE | 2026-03-04
|  |  |  | Extend struct proc with priority, wait_ticks, cpu_ticks | Taksh | TRUE | 2026-03-06
|  |  |  | Implement scheduler skeleton | Taksh | TRUE | 2026-03-08 | No behavior change yet
|  |  |  | Define initial alpha and beta parameters | Taksh | TRUE | 2026-03-10
|  |  |  | Study xv6 paging implementation in vm.c | Aditya | TRUE | 2026-03-04
|  |  |  | Study fork() memory behavior | Aditya | TRUE | 2026-03-04
|  |  |  | Add reference counting array ref_count[PHYSTOP/PGSIZE] | Aditya | TRUE | 2026-03-07
|  |  |  | Draft Copy-On-Write page fault design | Aditya | TRUE | 2026-03-10
|  |  |  | Implement memory allocation structures | Mayank | TRUE | 2026-03-06
|  |  |  | Study kalloc.c | Mayank | TRUE | 2026-03-04
|  |  |  | Add dynamic memory tracking structures | Mayank | TRUE | 2026-03-06
|  |  |  | Design memory compaction algorithm | Mayank | TRUE | 2026-03-08
|  |  |  | Design basic file abstraction structure | Ved Mitra | TRUE | 2026-03-04
|  |  |  | Implement file creation and deletion stubs | Ved Mitra | TRUE | 2026-03-07
|  |  |  | Design garbage collector mechanism | Ved Mitra | TRUE | 2026-03-09
|  |  |  | Add system call stubs for file operations | Ved Mitra | TRUE | 2026-03-10
|  | 2026-03-02 | 2026-03-08 | DELIVERABLE: Kernel boots without regression | Team | TRUE |  | Milestone 1
2 | 2 |  |  | Core Logic Implementation |  | TRUE |  | Goal: Functionality visible via logs
|  |  |  | Scheduler selects highest priority process | Taksh | TRUE | 2026-03-13
|  |  |  | Fork shares memory pages using COW | Aditya | TRUE | 2026-03-14
|  |  |  | File creation, read, write, and deletion operations implemented | Ved Mitra | TRUE | 2026-03-15
|  |  |  | Garbage collector detects unused memory blocks | Ved Mitra | TRUE | 2026-03-16
|  | 2026-03-09 | 2026-03-15 | DELIVERABLE: Arithmetic and logical processes successfully executed | Team | TRUE |  | Milestone 2
3 | 2026-03-04 |  |  | Integration & Synchronization |  | TRUE |  | Goal: Edge cases & cross-feature sync
|  |  |  | Freeze struct proc layout | Taksh/Aditya | TRUE | 2026-03-18 | Touchpoint Conflict Check
|  |  |  | Resolve memory inconsistency (Shared allocation interface) | Mayank/Aditya | TRUE | 2026-03-23
|  |  |  | Resolve file storage fragmentation (Memory compaction logic) | Ved/Mayank | TRUE | 2026-03-20
|  |  |  | Resolve GC timing conflicts (Run GC during idle cycles) | Taksh/Ved | TRUE | 2026-03-22
|  |  |  | Ensure no starvation under scheduler stress tests | Team | TRUE | 2026-03-29
|  |  |  | COW memory stable under concurrent writes | Team | TRUE | 2026-03-30 | Spinlocks / Race conditions
|  |  |  | File manager integrated with dynamic memory system | Team | TRUE | 2026-04-01
|  |  |  | Garbage collector safely frees unused memory | Team | TRUE | 2026-04-03
|  |  |  | Memory compaction reduces fragmentation | Team | TRUE | 2026-04-03
|  | 2026-03-16 | 2026-03-29 | DELIVERABLE: No kernel panics under combined workloads | Team | FALSE |  | Milestone 3
4 | 5 |  |  | Testing, Polish & Demo |  | FALSE |  | Goal: Full validation & Handover
|  |  |  | Scheduler performance validated | Taksh | FALSE
|  |  |  | Copy-On-Write memory stress tests pass | Aditya | TRUE | 2026-04-03
|  |  |  | File operations validated with multiple processes | Ved Mitra | TRUE | 2026-04-03
|  |  |  | Garbage collection successfully reclaims memory | Ved Mitra | TRUE | 2026-04-03
|  |  |  | Memory compaction verified during idle state | Mayank | TRUE | 2026-04-03
|  |  |  | Final Documentation & QEMU Demo Prep | Team | FALSE
|  | 2026-03-30 | 2026-04-05 | FINAL DELIVERABLE: QEMU demo prepared | Team | FALSE |  | Milestone 4
Risk Register Strategy:
Risk Item | Likelihood | Impact | Mitigation Strategy | Status
alpha/\beta instability | Medium | Medium | Parameter tuning during testing
COW race on ref_count | High | High | Spinlocks for synchronization
Memory fragmentation | Medium | Medium | Dynamic compaction algorithm
Garbage collection timing issues | Medium | Medium | Run GC during idle CPU cycles
QEMU memory limit | Low | Medium | Define memory constraints early

## Test-Ved (File-Garbage)
TEST CASE PLANNING AND EXECUTION TEMPLATE | [7 empty] | Link
TEST TITLE |  |  | PRIORITY | TEST CASE ID | TEST NUMBER | TEST DATE |  | https://drive.google.com/drive/folders/1V8HOMYdrgVYDHMzxMu7W7FmhA2kdswpy?usp=sharing
Create/Deleting of in memory File |  |  | HIGH | TC_F_GC | 1 | 2026-03-10
TEST DESCRIPTION |  |  | TEST DEPENDENCIES |  | TEST CONDITIONS | TEST CONTROL
Creation and deletion of in-memory file |  |  | syscall.c, kalloc.c, file.c, file.h, sysfile..c |  | XV-6 successfully booted | Manual Execution
STEP ID | STEP DESCRIPTION | TEST DATE | EXPECTED RESULTS | ACTUAL RESULTS | PASS/FAIL | ADDITIONAL NOTES | FINAL VERDICT
S1 | Create a in Memory File | 2026-03-10 | create a in memory file | failure to create a file | FAIL | incorrect struct mftable implementation | Completed
S1 | Create a in Memory File | 2026-03-10 | create an in-memory file | created an in memory file | PASS | corrected struct mftable (REQ-FILE-1, REQ-FILE-4)
S2 | Delete a in Memory File | 2026-03-12 | deletion in memory file | deleted an in memory file | PASS | all good (REQ-FILE-3)
TEST CASE PLANNING AND EXECUTION TEMPLATE
TEST TITLE |  |  | PRIORITY | TEST CASE ID | TEST NUMBER | TEST DATE
Reading/Writing in-Memory FIle + Garbage Collection |  |  | HIGH | TC_F_GC | 2 | 2026-03-18
TEST DESCRIPTION |  |  | TEST DEPENDENCIES |  | TEST CONDITIONS | TEST CONTROL
Read and write in in-memory file |  |  | syscall.c, kalloc.c, file.c, file.h, sysfile..c, gc.c |  | XV-6 successfully booted | Manual Execution
STEP ID | STEP DESCRIPTION | TEST DATE | EXPECTED RESULTS | ACTUAL RESULTS | PASS/FAIL | ADDITIONAL NOTES | FINAL VERDICT
S1 | Create a in Memory File | 2026-03-18 | create an in-memory file | created an in-memory file | PASS | Proof added now Displayes the address at which file is created (REQ-FILE-1, REQ-FILE-4) | Completed
S2 | Write in in-Memory File | 18 Marhc,2026 | write in-memory file | wrote in in-memory file | PASS | Proof added shows the message that is written and also the after address (REQ-FILE-2)
S3 | Read in-Memory File | 2026-03-18 | read in-memory file | read from in-memory file | PASS | Proof that it reads from the memory address (REQ-FILE-2)
S4 | Mark to be deleted in-Memory File | 2026-03-18 | Mark for deletion | Marked for deletion | PASS | (REQ-FILE-3)
S5 | Garbage Collector | 2026-03-18 | in-memory file deletion | in-memory file deleted | PASS | (REQ-GC-1, REQ-GC-2)

## Test-Taksh (Scheduler)
TEST CASE PLANNING AND EXECUTION TEMPLATE | [7 empty] | Link
TEST TITLE |  |  | PRIORITY | TEST CASE ID | TEST NUMBER | TEST DATE |  | https://drive.google.com/drive/folders/1k9AxFYt7aSfepQGnrJO5Mnl5RwFhZ91-?usp=sharing
Testing logic of dynamic priority scheduling algorithm |  |  | High | TC_SCH | 1 | 2026-05-03
TEST DESCRIPTION |  |  | TEST DEPENDENCIES |  | TEST CONDITIONS | TEST CONTROL
The test case focuses on verification of logic and implementation of scheduling algorithm |  |  | Test depends on getpriority syscall implementation
STEP ID | STEP DESCRIPTION | TEST DATE | EXPECTED RESULTS | ACTUAL RESULTS | PASS/FAIL | ADDITIONAL NOTES | FINAL VERDICT
S1 | Boot xv6 using make qemu-nox | 2026-03-05 | Kernel boots, $ prompt appears, no panic | Kernel booted successfully | PASS | REQ-SCH-1 | Completed
S2 | Run: schedtest | 2026-03-18 | Parent PID=3 spawned with Priority=50 | PID=3 Priority=50 confirmed | PASS | REQ-SCH-1
S3 | Observe start priorities of all children | 2026-03-18 | All 3 children start at Priority=50 | PID=4,5,6 all started at 50 | PASS | REQ-SCH-1
S4 | Observe end priorities and deltas | 2026-03-18 | All deltas negative (priority decreased) | Deltas: -15, -15, -30 all negative | PASS | REQ-SCH-3
S5 | Observe finish order of children | 2026-03-18 | Non-sequential order (not 4 to 5 to 6) | Order was 4 to 6 to 5, dynamic reordering confirmed | PASS | REQ-SCH-4
S6 | Confirm no kernel panic | 2026-03-18 | $ prompt returns cleanly after test | $ prompt returned, no panic | PASS | NFR-QUAL-4
TEST CASE PLANNING AND EXECUTION TEMPLATE
TEST TITLE |  |  | PRIORITY | TEST CASE ID | TEST NUMBER | TEST DATE
Testing multiprocess handling |  |  | High | TC_SCH | 2
TEST DESCRIPTION |  |  | TEST DEPENDENCIES |  | TEST CONDITIONS | TEST CONTROL
The test case focuses on handling of multiple processes
STEP ID | STEP DESCRIPTION | TEST DATE | EXPECTED RESULTS | ACTUAL RESULTS | PASS/FAIL | ADDITIONAL NOTES | FINAL VERDICT
S7 | Spawn one low-priority and two high-priority processes | PLANNED | All 3 processes created, low-priority starts at lower value | - | PLANNED | REQ-SCH-2 | Ongoing
S8 | Observe low-priority process priority incrementing while waiting | PLANNED | Priority increases by alpha=1 each wait tick | - | PLANNED | REQ-SCH-2
S9 | Verify low-priority process eventually gets scheduled and completes | PLANNED | Process finishes, no starvation observed | - | PLANNED | REQ-SCH-4
S10 | Run a CPU-bound process spanning multiple W windows | PLANNED | Process runs beyond 50 ticks | - | PLANNED | REQ-SCH-5
S11 | Verify cpu_ticks and window_ticks reset at W boundary | PLANNED | Both counters return to 0 after 50 ticks | - | PLANNED | REQ-SCH-5
S12 | Verify is_cpu_bound flag clears after window reset | PLANNED | Process not permanently penalised across windows | - | PLANNED | REQ-SCH-5

## Test-Aditya(CoW)
TEST CASE PLANNING AND EXECUTION TEMPLATE | [7 empty] | Link
TEST TITLE |  |  | PRIORITY | TEST CASE ID | TEST NUMBER | TEST DATE |  | https://drive.google.com/drive/folders/1B2jr2uR7wX3gWmDpaAwzX1YJ6EhPpYlN?usp=sharing
Testing CoW implementation |  |  | High | TC_CoW | 1 | 2026-12-03
TEST DESCRIPTION |  |  | TEST DEPENDENCIES |  | TEST CONDITIONS | TEST CONTROL
The test case focuses on testing the correctness of the implementation of CoW |  |  | The test case depends on the ref_count array
STEP ID | STEP DESCRIPTION | TEST DATE | EXPECTED RESULTS | ACTUAL RESULTS | PASS/FAIL | ADDITIONAL NOTES | FINAL VERDICT
S1 | Creating a process variable | 2026-11-03 | Before fork: 10 | Before fork: 10 | PASS | REQ-MEM-3 | Completed
S2 | Creating a child process | 2026-12-03 | Before fork: 10 Child sees: 10 | Before fork: 10 Child sees: 10 | PASS | REQ-MEM-1
S3 | Child process changing the value of the variable | 15-3-2026 | Before fork: 10 Child sees: 10 Child changed to: 20 | Before fork: 10 Child sees: 10 Child changed to: 20 | PASS | REQ-MEM-2&4
S4 | Accessing the parent variable after child process change | 18-3-2026 | Before fork: 10 Child sees: 10 Child changed to: 20 Parent sees after child: 10 | Before fork: 10 Child sees: 10 Child changed to: 20 Parent sees after child: 10 | PASS | REQ-MEM-2&4

## Test-Mayank (Memory-Allocation)
TEST CASE PLANNING AND EXECUTION TEMPLATE | [7 empty] | Link
TEST TITLE |  |  | PRIORITY | TEST CASE ID | TEST NUMBER | TEST DATE |  | https://drive.google.com/drive/folders/1_lOyDhe4oiA6DQ6QgZE7Ph4In1Svasxy?usp=sharing
Memory Compaction Algorithm Validation |  |  | High | TC_MEM_ALLOC | 1 | -
TEST DESCRIPTION |  |  | TEST DEPENDENCIES |  | TEST CONDITIONS | TEST CONTROL
Verify memory compaction relocates pages and reduces fragmentation. |  |  | compact.c, kalloc_below(), vm.c, proc.c |  | Multiple processes active | Multiple processes active
STEP ID | STEP DESCRIPTION | TEST DATE | EXPECTED RESULTS | ACTUAL RESULTS | PASS/FAIL | ADDITIONAL NOTES | FINAL VERDICT
S1 | Kernel logs + manual observation | Planned | Compaction start message printed | - | - | - | Ongoing

## Test - Template
TEST CASE PLANNING AND EXECUTION TEMPLATE
TEST TITLE |  |  | PRIORITY | TEST CASE ID | TEST NUMBER | TEST DATE
TEST DESCRIPTION |  |  | TEST DEPENDENCIES |  | TEST CONDITIONS | TEST CONTROL
STEP ID | STEP DESCRIPTION | TEST DATE | EXPECTED RESULTS | ACTUAL RESULTS | PASS/FAIL | ADDITIONAL NOTES | FINAL VERDICT
Few Points to remember:
1. In test Case ID: follow the same naming form (TC_SCH, TC_Cow, TC_MEM_ALLOC, TC_F_GC)
2. add you test to the test table in implementation sheet